## Progress_Log
Date | Step | Task | Work Completed | Output File | Status | Problem/Issue | Next Action
2026-07-12 | Step 0 | Project folder setup | Complete folder structure 00-12 created | Main project folder | Completed | Placeholder files were zero-byte | Replace placeholders and begin Step 1
2026-07-12 | Step 0 | Replace zero-byte placeholders with valid Office files | Created valid Progress Log, Decision Log, Dataset Inventory, Concept Note, Full Report, Literature Matrix | 00_Project_Management; 01_Report; 02_Literature_Review | Completed |  | Proceed with Step 1 research foundation
2026-07-12 | Step 1 | Research foundation (title, scope, aim, objectives, questions) | Working title, study/temporal scope, aim, six objectives, and seven research questions drafted into Concept Note and Full Report | Research_Concept_Note_v01.docx; Full_Research_Report_v01.docx | In Progress |  | Review and finalize Step 1 before literature or data collection
12 July 2026 | Step 1 | Research foundation finalization | Finalized title, study scope, temporal scope, aim, objectives, questions, significance, expected outputs, contributions, and delimitations | Research_Concept_Note_v01.docx; Full_Research_Report_v01.docx | Completed | None | Begin Step 2 literature review and research-gap assessment
13 July 2026 | Step 2.1 | Literature search protocol | Created systematic literature-search rules, search themes, queries, inclusion/exclusion criteria and screening procedure | Literature_Search_Protocol_v01.docx; Literature_Review_Matrix.xlsx | Completed | None | Begin Step 2.2 Litmaps seed-paper mapping
13 July 2026 | Step 2.2 | Litmaps setup and first seed paper | Core Litmap completed with 8 seed papers including Salemi (2025) high-resolution causal land-cover working paper | Literature_Review_Matrix.xlsx; litmaps_step_2_2_* screenshots through eighth_seed_salemi_causal_v01.png | Completed — 8 core seed papers added | None | Begin Step 2.3 related-paper discovery and screening
13 July 2026 | Step 2.2 | Third Litmaps seed paper | Hassan et al. (2023) verified and added; tags Seed Paper, Direct Forest Change, Fragmentation; Matrix P003; Search Log S003; screenshot saved | Literature_Review_Matrix.xlsx; litmaps_step_2_2_third_seed_fragmentation_v01.png | Completed | None | Add the core machine-learning seed paper
13 July 2026 | Step 2.2 | Fourth Litmaps seed paper | Added Rahaman et al. (2022) ML seed paper; tags Seed Paper, Direct Forest Change, Machine Learning; P004 and S004 recorded; screenshot saved | Literature_Review_Matrix.xlsx; litmaps_step_2_2_fourth_seed_machine_learning_v01.png | Completed | None | Continue core seed collection or begin Explore Related Articles when ready
13 July 2026 | Step 2.2 | Fifth Litmaps seed paper | Added Mahmood et al. (2025) biomass, carbon-stock and restoration study | Literature_Review_Matrix.xlsx; litmaps_step_2_2_fifth_seed_biomass_carbon_v01.png | In Progress — 5 core seed papers added | None | Add the recent landscape-fragmentation seed paper
13 July 2026 | Step 2.2 | Sixth Litmaps seed paper | Added Mitra et al. (2025) recent landscape-fragmentation study | Literature_Review_Matrix.xlsx; litmaps_step_2_2_sixth_seed_recent_fragmentation_v01.png | In Progress — 6 core seed papers added | None | Add the Synthetic Difference-in-Differences methodological seed paper
13 July 2026 | Step 2.2 | Seventh Litmaps seed paper | Added Arkhangelsky et al. (2021) Synthetic Difference-in-Differences methodological paper | Literature_Review_Matrix.xlsx; litmaps_step_2_2_seventh_seed_sdid_v01.png | In Progress — 7 core seed papers added | None | Add the high-resolution causal land-cover working paper
13 July 2026 | Step 2.2 | Eighth Litmaps seed paper | Added Salemi working paper on high-resolution causal land-cover change | Literature_Review_Matrix.xlsx; litmaps_step_2_2_eighth_seed_salemi_causal_v01.png | Completed — 8 core seed papers added | None | Begin Step 2.3 related-paper discovery and screening
13 July 2026 | Step 2.3A | First related-paper discovery batch | Recorded metadata for the first ten Litmaps recommendations | Literature_Review_Matrix.xlsx; litmaps_step_2_3_first_discovery_batch_v01.png | Completed — discovery batch recorded | None | Proceed with Litmap addition of included candidates P009–P018
13 July 2026 | Step 2.3B | Screen candidates C001–C010 and sync master matrix | All ten discovery candidates marked Added to Litmap=Yes; master Literature_Matrix expanded to P001–P018 | Literature_Review_Matrix.xlsx; litmaps_step_2_3_included_papers_tagged_v01.png | Completed | None | Begin Step 2.4 metadata verification and full-text collection for P001–P019
13 July 2026 | Step 2.3C | Litmap and master-matrix reconciliation | Identified Rashid et al. (2021) as an additional relevant saved article and assigned C011/P019. | Literature_Review_Matrix.xlsx | Completed | None | Begin Step 2.4 metadata verification and full-text collection for P001–P019
13 July 2026 | Step 2.4A | P001 metadata verification and full-text extraction | Verified official metadata; downloaded and reviewed the full text; extracted objective, study area, datasets, preprocessing, Random Forest configuration, accuracy, findings, author-stated limitations, critical gaps, and relevance to the proposed study. | P001_2018_hassan_extraction_notes.docx; Literature_Review_Matrix_P001_Completed.xlsx; 2018_hassan_rohingya_refugee_crisis_forest_cover_change.pdf | Completed | None | Begin Step 2.4B: P002 Dampha et al. (2022) metadata verification and full-text extraction
13 July 2026 | Step 2.4B | P002 metadata verification and full-text extraction | Verified official metadata and extracted datasets, Random Forest classification, treatment-control design, DiD model, robustness tests, findings, limitations and research gap | P002_2022_dampha_extraction_notes.docx; Literature_Review_Matrix.xlsx | Completed | Detailed public appendices were unavailable; inconsistent settlement-area reporting was identified | Begin Step 2.4C — P003 Hassan et al. (2023)
16 July 2026 | Step 2.4C | P003 metadata verification and partial review | Verified metadata, abstract, publisher highlights and accessible section snippets. Recorded P003 as a partial review; complete full text was unavailable, so detailed methods, validation and findings remain conditional. | Literature_Review_Matrix.xlsx; Literature_Notes.docx | Partially Completed — Full Text Unavailable | Complete full text unavailable; only abstract, highlights and accessible section snippets could be verified. | Begin Step 2.4D — P004 metadata verification and partial extraction
16 July 2026 | Step 2.4D | P004 metadata verification and partial extraction | Verified official metadata, abstract, objectives, reported periods, machine-learning approaches, principal findings, prediction horizon, relevance, limitations and research gap | P004_2022_rahaman_partial_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx | Partially Completed — Full Text Unavailable | ScienceDirect full text requires paid access; detailed datasets, accuracy assessment and model settings could not be verified | Begin Step 2.4E — P005 metadata verification and full-text collection
16 July 2026 | Step 2.4E | P005 metadata verification and full-text extraction | Verified official metadata and extracted restoration context, sampling design, biomass-estimation procedures, five carbon pools, allometric models, numerical findings, limitations, relevance and research gap. | Research_Papers/03_Biomass_Carbon_Studies/2025_mahmood_tracking_forest_recovery_biomass_carbon.pdf; Paper_Extraction_Notes/P005_2025_mahmood_extraction_notes.docx; Literature_Review_Matrix.xlsx (P005); Literature_Notes.docx (Biomass and Carbon); P005_Extraction sheet | Completed | None blocking. Noted publisher Highlights AGB/BGB swap vs abstract/Table 6; species-count inconsistency abstract vs Results/Table 3; minor 93.90 vs 93.95 mean C wording. | Begin Step 2.4F — P006 Mitra et al. (2025)
16 July 2026 | Step 2.4F | P006 metadata verification and full-text extraction | Verified official metadata and extracted Sentinel-2 image dates, Random Forest design, training-validation samples, classification accuracy, LULC change, FRAGSTATS metrics, NDVI analysis, camp-level population relationships, restoration signals, limitations, research relevance and research gap. | Research_Papers/02_Fragmentation_Studies/2025_mitra_landscape_fragmentation_population_distribution.pdf; Paper_Extraction_Notes/P006_2025_mitra_extraction_notes.docx; Literature_Review_Matrix.xlsx (P006); Literature_Notes.docx (Fragmentation; Population and Drivers); P006_Extraction sheet | Completed | Only two dates were analysed; historical population data were unavailable; settlement change was used as a population proxy; Camp 15 forest-loss reporting differs slightly between the abstract and results text. | Begin Step 2.4G — P007 Arkhangelsky et al. (2021), Synthetic Difference-in-Differences methodological review.
16 July 2026 | Step 2.4G | P007 SDID methodological full-text review | Verified the journal metadata and reviewed the open revised manuscript; extracted panel requirements, unit weights, time weights, weighted fixed-effects estimator, identification logic, theoretical properties, bootstrap, jackknife and placebo inference, application limitations, required diagnostics and relevance to the proposed forest-loss attribution design. | P007_2021_arkhangelsky_sdid_extraction_notes.docx; Literature_Review_Matrix.xlsx; Research_Decision_Log.docx | Completed | The standard formulation uses binary treatment and does not automatically address spatial interference, continuous exposure, classification uncertainty or spatially correlated outcomes. | Begin Step 2.4H — P008 Salemi (2025) causal land-cover working paper.
16 July 2026 | Step 2.4H | P008 causal land-cover working-paper full-text review | Verified the latest author-hosted working-paper version and extracted Dynamic World data processing, treatment and spillover zones, propensity-score matching, event-study specification, fixed effects, spatially clustered standard errors, forest and settlement effects, protected-area and Kutupalong heterogeneity, robustness checks, nighttime-light analysis, intervention interpretation, limitations and implications for research novelty. | P008_2025_salemi_extraction_notes.docx; Literature_Review_Matrix.xlsx; Research_Decision_Log.docx | Completed | The paper is under review rather than peer reviewed; only two pre-treatment years are available; LPG and fencing effects cannot be separated; Dynamic World and nighttime-light measurement limitations remain. | Begin Step 2.4I — P009 Langer et al. (2015) methodological/restoration review.
16 July 2026 | Step 2.4I | P009 long-term refugee-camp environmental monitoring and restoration full-text review | Verified metadata and reviewed the open-access short paper; extracted the Lukole camp lifecycle, spatial buffer, Landsat archive, multi-sensor SIAM preprocessing, greenness index, object-based change detection, preliminary deforestation and reforestation findings, methodological advantages, limitations and relevance to long-term recovery analysis. | P009_2015_langer_extraction_notes.docx; Literature_Review_Matrix.xlsx; Research_Decision_Log.docx | Completed | The paper reports preliminary findings only; no quantitative deforestation/reforestation areas, accuracy assessment or uncertainty analysis are provided. Publisher and institutional records disagree on the volume number. | Begin Step 2.4J — P010 Hasan et al. (2020) full-text review.
16 July 2026 | Step 2.4J | P010 forest degradation, ecosystem-function loss and CA–Markov prediction full-text review | Verified final journal and online-first metadata; reviewed the author-uploaded full text; extracted study area, Sentinel-2A classification, forest-beat coverage, observed degradation, CA–Markov prediction, degradation drivers, biomass and carbon-stock methods, ecosystem-function implications, limitations and relevance to the proposed integrated research design. | P010_2021_hasan_extraction_notes.docx; Literature_Review_Matrix.xlsx; Research_Decision_Log.docx | Completed | Final issue year is 2021 although the paper was accepted and first published online in 2020; predicted 2027 loss is reported as both approximately 5,115 and 5,120 ha due to rounding. Automated binary PDF download from ResearchGate/Authorea was blocked by Cloudflare; full text was reviewed from author-uploaded public full text and an archival working PDF was saved. | Begin Step 2.4K — P011 Sarkar et al. (2023).
16 July 2026 | Step 2.4K | P011 ecological-impact, ecosystem-service and fuzzy-EQ full-text review | Verified metadata and reviewed the open full text; extracted Sentinel and Landsat inputs, WorldView/field reference sampling, ANN/RF/SVM settings and accuracy, LULC change, ESV methodology, sensitivity analysis, ecosystem-service results, fuzzy ecological-quality model, Markov transitions, limitations, inconsistencies, research relevance and research gap. | P011_2023_sarkar_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2023_sarkar_ecological_impact_refugee_crisis.pdf | Completed | The 2017 baseline coincides with the beginning of the major influx; the two images are seasonally mismatched; abstract and Table 5 contain conflicting raw-material and biodiversity percentages; the water-change narrative conflicts with Table 3. | Begin Step 2.4L — P012 Sarkar et al. (2022), ecosystem-service-cost review.
16 July 2026 | Step 2.4L | P012 ecosystem-service-cost full-text review | Verified final and online-first metadata; extracted ANN-based LULC classification, January 2017/2021 Sentinel dates, sample design, 2017–2021 forest and settlement change, benefit-transfer ESV framework, aggregate and service-specific monetary results, sensitivity analysis, limitations, relationship with P011 and implications for evidence independence. | P012_2023_sarkar_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2023_sarkar_cost_ecosystem_service_value.pdf | Completed | P011 and P012 share closely related LULC inputs but report materially different ESV totals and service-specific changes; the papers must not be treated as independent evidence. Automated RG binary PDF download blocked; author public full text reviewed and working archive saved. | Begin Step 2.4M — P013 Ahmed et al. (2024).
16 July 2026 | Step 2.4M | P013 long-term LULC, LST and CA–ANN prediction full-text review | Verified official metadata and reviewed the author-uploaded full article; extracted study domains, eight Landsat dates, iso-cluster classification, LST processing, CA–ANN/MOLUSCE design, calibration and validation, historical camp-area LULC and LST change, 2028 and 2034 predictions, limitations, methodological inconsistencies, research relevance and research gap. | P013_2024_ahmed_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2024_ahmed_rohingya_lulc_lst_machine_learning.pdf | Completed | Historical and predictive analyses use different spatial domains; the broad vegetation class is not forest-specific; only the 2022 LULC map received a reported accuracy assessment; the NDVI–LST R² value is described as a correlation coefficient; CA–ANN hyperparameters and uncertainty are incompletely reported. Binary author PDF download blocked — working archive saved. | Begin Step 2.4N — P014 Gromny et al. (2024) comparative remote-sensing methodological review.
16 July 2026 | Step 2.4N | P014 annual multi-sensor refugee-camp lifecycle and socioeconomic-driver full-text review | Verified metadata and reviewed the open-access full text; extracted the Mtendeli camp lifecycle, 40 × 40 km analysis area, distance buffers, WorldCover-derived training data, Sentinel-1, Sentinel-2 and Landsat processing, Random Forest annual mapping, validation design, land-cover transitions, distance-decay pattern, cropland and fuelwood drivers, qualitative interviews, camp-closure effects, restoration findings, limitations and relevance to the proposed Cox’s Bazar analysis. | P014_2024_gromny_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2024_gromny_mtendeli_land_cover_drivers.pdf | Completed | The time series lacks a clean long pre-camp baseline; only the 2020 annual map and July 2022 single-image classification have reported independent accuracy assessments; the legend changes in 2022; vegetation classes show confusion; qualitative driver evidence is not causal attribution. Automated OA/RG binary PDF download blocked — working archive saved. | Begin Step 2.4O — P015 Mohiuddin et al. (2025), elephant-route and land-cover conservation review.
18 July 2026 | Step 2.4O | P015 Rohingya-related LULC and elephant-route partial review | Verified official metadata and publisher abstract; extracted the 2016–2021 design, GIS software, Palong Khali and Teknaf forest and settlement changes, elephant-route interpretation, conservation relevance, methodological limitations, ambiguous casualty claim and research gap. | P015_2025_mohiuddin_partial_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx | Partially Completed — Full Text Unavailable | The Springer article requires subscription access. Satellite sensor, image dates, classification method, validation accuracy, complete LULC results and elephant-route analytical procedure could not be independently verified. The abstract contains an ambiguous casualty claim that will not be used without primary-source verification. | Begin Step 2.4P — P016 Chowdhury et al. (2025), ecological restoration review.
18 July 2026 | Step 2.4P | P016 reforestation recovery, resilience and land-use-legacy full-text review | Verified official metadata and reviewed the open full text; extracted Kutupalong restoration history, Sentinel-2 Random Forest mapping, classification accuracy, land-use legacy selection, 188-plot field inventory, tree composition, topographic variables, EVI recovery/resilience equations, linear mixed models, LULC changes, annual resilience dynamics, species-richness and elevation effects, limitations, policy implications and relevance to the proposed research. | P016_2025_chowdhury_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2025_chowdhury_land_use_legacy_reforestation_resilience.pdf | Completed | The study samples only successfully reforested trajectories, has no untreated control, uses three LULC dates and January-only EVI observations, and does not directly measure biomass, carbon, fragmentation, soil recovery or causal restoration effects. | Begin Step 2.4Q — P017 Liu et al. (2026), protected-area governance and conservation review.
18 July 2026 | Step 2.4Q | P017 protected-area governance, ecological-threshold and future-scenario full-text review | Verified official metadata and reviewed the open-access Version of Record; extracted the 2016–2024 LULC design, Landsat/Sentinel processing, field evidence, InVEST 3.18.0 habitat-quality model, NDVI and LST, landscape-pattern analysis (PD/LPI/ED), protected-area boundary gradient (100/300/500/1000/2000 m buffers), the 300–500 m critical transition zone, PLUS v1.4.2 2036 business-as-usual simulation, zoning and regeneration strategy, limitations, research relevance and gap. | P017_2026_liu_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2026_liu_land_use_governance_protected_areas.pdf | Completed | The design includes only one pre-influx year and four observed dates; the 300–500 m spatial threshold is diagnostic rather than causal; InVEST and PLUS results depend on parameter assumptions; a single 2024-trained RF (OA 80.2%/κ 0.73) is applied to all years; no carbon accounting, SDID or jointly propagated uncertainty; the cited 54.6% forest / 598.5% settlement figures originate from P006 (Mitra et al.). | Begin Step 2.4R — P018 Sobczak-Szelc et al. (2026), background, migration and environmental-governance review.
18 July 2026 | Step 2.4R | P018 common-pool-resource, (mal)coping and socio-environmental-governance full-text review | Verified the final 2026 bibliographic record and reviewed the open-access full text; extracted the integrated socio-ecological framework, common-pool resources, transformative adaptation, adaptive governance, 34-interview qualitative design, eight sub-camps, NVivo analysis, supplementary Sentinel-2 dates, land/wood/water access, coping and (mal)coping, institutional fragmentation, four-phase resource-governance transformation, limitations, research relevance and research gap. | P018_2026_sobczak_szelc_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2026_sobczak_szelc_common_pool_resources_malcoping.pdf | Completed | The study is qualitative and male-dominated, covers a limited number of participants and sub-camps, and uses three Sentinel-2 images only as supplementary visual evidence. It provides no validated forest-loss quantity, fragmentation, carbon estimate or causal environmental effect. The Taylor & Francis binary PDF was Cloudflare-blocked; the full text was reviewed from the open-access HTML version of record and a working archival PDF was saved to be replaced with the official publisher PDF later. | Begin Step 2.4S — P019 Rashid et al. (2021), vegetation and land-surface-temperature full-text review.
18 July 2026 | Step 2.4S | P019 vegetation-loss and land-surface-temperature full-text review | Verified the final 2021 journal record and reviewed the complete author-uploaded full text (RG personal copy); extracted Landsat dates, QGIS/SCP preprocessing, Random Forest (dzetsaka) classification, three LULC classes, OOB and Google Earth validation, post-classification transitions, gross (1,876.14 ha) and net (~836.46 ha) vegetation loss, Planck/NDVI-emissivity LST method, BMD comparison, class-specific thermal results, methodological limitations, internal inconsistencies, relevance and research gap. | P019_2021_rashid_extraction_notes.docx; Literature_Review_Matrix.xlsx; Literature_Notes.docx; Research_Decision_Log.docx; 2021_rashid_vegetation_lst_rohingya_camps.pdf | Completed | Broad vegetation class is not forest-specific; gross loss is sometimes described as forest loss; accuracy values differ across sections; maximum LST reported inconsistently (abstract ~34 °C vs table 35.7 °C); TIRS Bands 10 and 11 averaged; station air temperature is not direct LST validation; no causal design or propagated uncertainty. Springer subscription + RG login-gated binary; reviewed from author personal copy, working archival PDF saved to replace with the author/publisher PDF later. | Close Step 2.4 (all 19 papers reviewed: 16 full-text, 3 partial-access) and begin Step 2.5 — Cross-Paper Evidence Synthesis, Quality Appraisal and Gap Matrix.
19 July 2026 | Step 2.5A | Evidence family audit and non-independence control | Built Evidence_Families (18 families) and Synthesis_Register (19 papers P001-P019) in the master matrix without altering existing sheets; classified independence, overlap (P011/P012), methodological (P007), partial-access (P003/P004/P015), comparative and qualitative evidence; added Decision 023. | Literature_Review_Matrix.xlsx (Evidence_Families, Synthesis_Register); Research_Decision_Log.docx (Decision 023) | Completed | None | Begin Step 2.5B - Methodological Quality Appraisal (standardized quality scoring of all 19 papers)
19 July 2026 | Step 2.5B | Standardized methodological quality appraisal of all 19 papers | Scored all reviewed papers across objective–design fit, data transparency, temporal adequacy, spatial/sample adequacy, measurement validity, validation and robustness, uncertainty handling and claim–method alignment. Normalized scores were calculated using applicable domains, while access status, direct relevance, causal status and independence were recorded separately. | Literature_Review_Matrix.xlsx (Quality_Rubric, Quality_Appraisal); Research_Decision_Log.docx (Decision 024) | Completed | Three papers remain partial-access and were capped at Moderate. Several studies are highly relevant but temporally limited, while some high-quality comparative or methodological papers are not direct Cox's Bazar outcome evidence. | Begin Step 2.5C — Cross-Paper Thematic Evidence Synthesis.
19 July 2026 | Step 2.5C1 | Core environmental-outcome thematic synthesis | Synthesised forest and vegetation loss, fragmentation and connectivity, biomass and carbon, and restoration and resilience evidence using methodological quality, relevance and independence. Created an evidence-conflict register and separated forest from vegetation, gross from net loss, and greenness from carbon recovery. | Literature_Review_Matrix.xlsx (Thematic_Synthesis, Evidence_Conflicts); Research_Decision_Log.docx (Decision 025) | Completed | Numerical pooling is not appropriate because outcome definitions, spatial domains, observation periods and designs differ. Partial-access, proxy, comparative and overlapping evidence remains conditional or separately labelled. | Begin Step 2.5C2 — Causal, predictive, governance and conservation evidence synthesis.
19 July 2026 | Step 2.5C2 | Causal, predictive, governance and conservation evidence synthesis | Synthesised causal attribution, prediction/LST/habitat risk, socioeconomic governance, and biodiversity/protected-area/elephant-corridor evidence. Added conflict controls separating causal estimates, scenarios, interventions, habitat-quality indices and corridor overlap. | Literature_Review_Matrix.xlsx (Thematic_Synthesis T05-T08, Evidence_Conflicts C06-C10); Research_Decision_Log.docx (Decision 026) | Completed | Causal effect sizes and scenarios remain non-combinable; intervention and corridor evidence is mechanism/prioritisation evidence rather than direct causal proof. | Begin Step 2.5D — Research Gap and Novelty Matrix.
19 July 2026 | Step 2.5D | Research gap and evidence-bounded novelty matrix | Mapped twelve research gaps against the reviewed literature, identified the strongest existing evidence and methodological limitations, linked proposed contributions to current data feasibility, and separated locked, conditional and supporting contributions. Created a novelty-claims register containing allowed wording, prohibited wording and conditions for final use. | Literature_Review_Matrix.xlsx (Research_Gap_Matrix, Novelty_Claims_Register); Research_Decision_Log.docx (Decision 027) | Completed | Several contributions remain conditional on annual exposure reconstruction, covariate collection, SDID diagnostics, carbon calculations, uncertainty propagation, predictive validation and verified conservation layers. | Begin Step 2.5E — Final Literature Synthesis and Research Design Lock.
19 July 2026 | Step 2.5E | Final literature synthesis and research-design lock | Finalised six synthesis sections and provisionally locked the working title, aim, six objectives, six research questions, primary datasets, analytical roles, evidence-bounded novelty and conditional items. Locked measurement, causal attribution, prediction, mechanism and conservation roles separately. | Literature_Review_Matrix.xlsx (Final_Literature_Synthesis, Research_Design_Lock); Research_Decision_Log.docx (Decision 028) | Completed | The 2001-2025 framework is retained, but Hansen GFC v1.12 is confirmed through 2024 only; annual 2025 outcome remains conditional. Camp footprints, covariates, donor refinement, uncertainty, SHAP and conservation layers require empirical refinement. | Begin Step 3.2 — Annual Forest Outcome Dataset Construction, while refining D04 donor covariates and treatment definitions.
19 July 2026 | Step 2.6 | Final literature QA, consistency audit and freeze | Verified D01–D12 source datasets and RC01–RC05 research components, P003 partial-access status, P011/P012 suffixes, Hansen 2001–2024 confirmed / 2025 conditional wording, cautious donor language, carbon-method condition, decision/progress alignment, formula errors, duplicate IDs and unsupported claims. Final result: Literature Phase: Verified and Frozen. | Research_Decision_Log.docx (Decision 029); Literature_Review_Matrix.xlsx; Dataset_Inventory.xlsx; Research_Progress_Log.xlsx | Completed | No critical inconsistency remained after the final audit. The literature phase can reopen only under Decision 029 conditions. | Begin Step 3.2 — Empirical Dataset Construction: 2016–2017 camp-footprint reconstruction; 2018 official-boundary validation; RC04 donor covariate refinement; full Hansen 2001–2024 extraction; annual 1 km forest-outcome table; JRC TMF validation; fragmentation pilot.